## New Rows Dev3
Enviroment | Portal | Tested Features and Functions Task | Check | Double Check | Task Status | Notes
Dev3 | Origination | Merchant Page: Search Filters (Merchant Category field) | Yuri | Lucas | Done | Merchant Category field tested (search)
Dev3 | Origination | Merchant Page: Search Filters (Active field) | Yuri | Lucas | Done | Active field tested (search) - Search for Active and Inactive Merchants
Dev3 | Origination | Merchant Page: Add merchant + add program + validation log | José | Yuri | Done | TST1-0001 FlexShopper, Anory Store - GOW0001 (UOWN), Ashby Store - GOW0002 (Kornerstone)
Dev3 | Origination | Merchant Page: Search Filters (Search field) | Yuri | Lucas | Done | Seach field tested with merchantCode, merchantName, locationName, zipCode - (Search Field dont work for City, State, email, contact name, etc)
Dev3 | Origination | Merchant Page: Remove program + validate log | José | Yuri | Done | TST1-0001 FlexShopper - Removed Merchant Program: 2021 OH,PA,IA,CO,MA Program SAC from Merchant
Dev3 | Origination | Merchant Page: Search Filters (Sales Rep Code field) | Yuri | Lucas | Done | Sales Rep Code Field tested (search)
Dev3 | Origination | Leads Page: Search leads using filters by date + merchants + Locations | José | Lucas | Done
Dev3 | Origination | Merchant Page: Clone | Yuri | Lucas | Done | Tested clone, UOWN and KORNERSTONE
Dev3 | Origination | State Configs: State Configurations | Lucas | Yuri | Done | Search, edit and input validations tested
Dev3 | Origination | Funding Page: Funding Queue | Lucas | Yuri | Done | List, select and send to funding functions tested
Dev3 | Origination | Programs Page: Program Settings | Lucas |  | Waiting Double Check | List and batch edit functions tested
Dev3 | Origination | Complete Application Flow | Lucas |  | Done | Received the error "Request processing failed: org.springframework.transaction.UnexpectedRollbackException: Transaction silently rolled back because it has been marked as rollback-only" in the send application flow after clicking submit when entering the card details.
Dev3 | Customer Portal | Receive Verification Code Flow | Lucas |  | Done
Dev3 | Servicing | Customer Information Page (Primary Applicant + Primary Contact) | Lucas |  | Waiting Double Check | Primary Info edition tested
Dev3 | Servicing | Customer Information Page (Bank Account) | Lucas |  | Waiting Double Check | Bank Account Info edition tested
Dev3 | Servicing | Customer Information Page (Servicing Information) | Lucas |  | Waiting Double Check | Editable fields tested
Dev3 | Servicing | Customer Information Page (Make Payment - ACH) | Lucas |  | Waiting Double Check | Make ACH Payment tested
Dev3 | Servicing | Customer Information Page (Make Payment - CC) | Lucas |  | Waiting Double Check | Make CC Payment tested
Dev3 | Servicing | Customer Information Page (Payment Transactions) | Lucas |  | Waiting Double Check | List all the transactions made
Dev3 | Origination | SendApplication 13m UOWN and KORNERSTONE | José |  | Waiting Double Check | Lead Approved -> funding. Validated Log
Dev3 | Origination | Application flow | Mumu |  | Waiting Double Check | Full process of an application
Dev3 | Origination | Error Log Page | José | Lucas | Done | Send/Submit Application tabs + download CSV
Dev3 | Origination | Funding Modification History | José | Lucas | Done | Search + CSV/Email export
Dev3 | Origination | Modification Report Page | José | Lucas | Done | Search + Email CSV
Dev3 | Origination | Program Group Page | José | Lucas | Done | Listing + inline name edit
Dev3 | Origination | Rebate Page | José | Lucas | Done | Search + Download CSV
Dev3 | Origination | Open To Buy Page | José | Lucas | Done | Search + Email CSV
Dev3 | Origination | Merchant Setting | José | Lucas | Done | Edit 247 merchants
Dev3 | Servicing | Quick Search | José |  | Waiting Double Check | Search by name/phone + filters
Dev3 | Servicing | Documents Page | José |  | Waiting Double Check | Document viewing and download
Dev3 | Servicing | Move Due Dates | José |  | Need Fix | "status":404,"error":"Not Found","message":"No static resource uown/svc/moveDueDatesByDays/223.","path":"/uown/svc/moveDueDatesByDays/223/"}
Dev3 | Origination | Overview Page: Metrics + date filters + CSV export | José |  | Done | Search in metrics CSV export OK; all endpoints 200
Dev3 | Servicing | Add Fee | José |  | Waiting Double Check | Create manual fee
Dev3 | Servicing | scheduled payment | José |  | Waiting Double Check | Create scheduled payment
Dev3 | Servicing | Payment Arrangement | José |  | Waiting Double Check | View + full lifecycle (accounts 166 and 187) - Cycle mapped: NOT_STARTED / IN_PROGRESS / SUCCESS / FAILED. Creating CC arrangement auto-sets rating to P and disables CC+ACH autopay; reverts on SUCCESS.
Dev3 | Servicing | Frequency Changes History | José |  | Done | AccountPk 166
Dev3 | Servicing | Items Purchased History | José |  | Done | AccountPk 166
Dev3 | Servicing | Search Page | José |  | Done | Search accounts
Dev3 | Servicing | Customer Information Page | José |  | Waiting Double Check | Financial overview + consistency check - accounts 104 and 138 - Opening any account auto-creates a review log entry - financials internally consistent; concatenated alert text
Dev3 | Origination | Alert Page | José |  | Waiting Double Check | Search + CSV/Email export - Returned real records (status + approval amount changes); CSV and Email CSV export OK
Dev3 | Origination | Blacklist Page | José |  | Waiting Double Check | Search + add form (card BIN) - 1 test record with SSN + bank data unmasked; BIN field accepts 5 digits with Save enabled
Dev3 | Origination | Calculator prorated amount | José |  | Waiting Double Check | Modal with AS OF date; computes prorated early-payoff amount
Dev3
Dev3
Dev3
Dev3
Dev3
Dev3
Dev3